## Budget Summary
FINA-3039-01 Budgeting and Financial Issues November 29, 2013 Travis Vanos
Seacrest Industries - November 2013 Workstation Deployment Project Project Budget Summary
Seacrest Industries - Workstation Deployment Project Budget Summary | [5 empty] | Project Scope Assumption
Cost Area | Initial Costs | Year 1 | Year 2 | Year 3 | Total | As Equilibrium Consulting, we are providing Seacrest Industries with the following: • 100 Workstations evenly distributed across four regions (Western, Ontario, Québec, and Atlantic) • The Workstation setups include a laptop for employee mobility, a laptop lock for security, a monitor, a keyboard, and a mouse (for when employees are working at a desk). The hardware deployment at each site will take 2 weeks, with a buffer of 1 week to account for travel between regions. Seacrest Industries will handle the required support personnel post-workstation deployment. All of the necessary furniture, electrical, and networking requirements are already in place, or will be handled by Seacrest Industries. Each employee laptop will have a system image applied that includes the required software based on their job role, as per Seacrest Industries' internal IT policy. It is assumed that Seacrest Industries already has the required volume licensing for the required employee software. A required 1-Year support contract is included in this project. Within this contract, Equilibrium Consulting will provide 24 hours a day, 7 days a week, 365 days a year technical support (by phone and email) for all issues relating to the deployed hardware. For any issues that cannot be solved by our technical team, we will liaison with the appropriate vendor.
Labour | 320329 | 0 | 0 | 0 | 320329
Hardware | 142863 | 200 | 1047.5 | 118226.24 | 262336.74
Consulting Fees | 13560 | 0 | 0 | 0 | 13560
Initial Cost and Yearly Totals | 476752 | 200 | 1047.5 | 118226.24 | 596225.74
Overhead Cost |  |  |  |  | 89433.861
Contingency Reserve |  |  |  |  | 68565.9601
Total Cost of Ownership for 3 Years |  |  |  |  | 754225.5611
Assumptions
- The funds for this project are assumed to be paid upfront by Seacrest Industries. - We assume that the budget is sufficient enough in order to complete the project, while meeting the end goals of Seacrest Industries. Although Seacrest Industries’ Management Team did not define a strict project cost, we have selected the optimal products for the project, while keeping the cost as low as we can without affecting the end result of the project. - The Overhead Indirect Cost is 15% of the direct project costs (Labour, Hardware, and Consulting Fees). - The Contingency Reserve is 10% of the project's total cost (including direct costs and the overhead cost). - All prices are in Canadian Dollars. - All product prices were valid as of November 29, 2013. - Product costs are based on corporate pricing. - We assume that our team is highly skilled, and does not require initial training on the products selected for this project. - All cost estimates are on corporate discounts available to Equilibrium Consulting due to our vendor relations.

## Labour Costs
Seacrest Industries - November 2013 Workstation Deployment Project Labour Costs
Labour Costs
Worker and Project Role | Pay/Hour | Hours Worked | Total
Justin Waelz - Team Leader | 130 | 480 | 62400
Serge Trunkin - Laptop Specialist | 120 | 480 | 57600
Anton Shylo - Laptop Accessory Specialist | 120 | 480 | 57600
Travis Vanos - Laptop Accessory Specialist | 120 | 480 | 57600
Travel Costs |  |  | 21063.2
Total |  | 1920 | 320329
Travel Cost per Deployment Region
Region | Travel Cost
| Hotel | Transportation | Total
Western Region | 5491.8 | 711.9 | 6203.7
Ontario Region | 4576.5 | 384.2 | 4960.7
Québec Region | 3661.2 | 1322.1 | 4983.3
Atlantic Region | 4068 | 847.5 | 4915.5
Total | 17797.5 | 3265.7 | 21063.2
Labour Cost per Deployment Region including Travel Costs
Worker | Western Region |  | Ontario Region |  | Québec Region |  | Atlantic Region
| Hours Worked | Cost | Hours Worked | Cost | Hours Worked | Cost | Hours Worked | Cost
Justin Waelz - Team Leader | 120 | 15600 | 120 | 15600 | 120 | 15600 | 120 | 15600
Serge Trunkin - Laptop Specialist | 120 | 14400 | 120 | 14400 | 120 | 14400 | 120 | 14400
Anton Shylo - Laptop Accessory Specialist | 120 | 14400 | 120 | 14400 | 120 | 14400 | 120 | 14400
Travis Vanos - Laptop Accessory Specialist | 120 | 14400 | 120 | 14400 | 120 | 14400 | 120 | 14400
Total Labour Cost per Region | 480 | 58800 | 480 | 58800 | 480 | 58800 | 480 | 58800
Total Labour Cost per Region including Travel |  | 65003.7 |  | 63760.7 |  | 63783.3 |  | 63715.5
Assumptions
- There are no ongoing yearly costs for this project regarding labour. - It is assumed that Seacrest Industries has the required IT staff at each location to support the deployment of the equipment purchased by Equilibrium Consulting. - The total cost of the internal labour includes 25% for benefits. The average hourly rates are based on skill level and project role. - No external labour is required for this project. - Travel costs, based on the distance from our headquarters in London, Ontario, are taken into consideration when calculating the total cost of labour. - The Hotels are booked using Equilibrium Consulting’s corporate discount, and include breakfast, lunch, and supper meals. The hotels selected also include laundry services. It is assumed that there will be two team members per room, with two beds per room. - Transportation services are provided at a discounted corporate rate. - Hotel and Transportation assumes a 3 week period (2 weeks on site, and a buffer of 1 week for travel time). - We assume that the team members work 8-hour days, with a 1-hour lunch break. - The individual hours are calculated based Analogous (or Top-Down) estimates, and have a built-in contingency in case tasks require more time than first thought. - The project’s Contingency Reserve will handle the cost of overtime if the need should arise.

## Hardware Costs
Seacrest Industries - November 2013 Workstation Deployment Project Hardware Costs
Hardware Costs
Hardware | Support | Cost/Unit | Quantity | Subtotal | Tax | Total
Lenovo ThinkPad T430 Laptop | 3 year Customer Replaceable Unit (CRU), and On-site 9x5 Next Business Day (NBD) support | 1024 | 100 | 102400 | 13312 | 115712
Targus DEFCON Serialized Laptop Locks (25 per Box) | 60 Day Warranty | 650 | 4 | 2600 | 338 | 2938
BenQ BL2201PU 22-inch Monitor | 60 Day Warranty | 189 | 100 | 18900 | 2457 | 21357
Logitech MK120 Desktop Keyboard and Mouse | 60 Day Warranty | 12 | 100 | 1200 | 156 | 1356
Shipping Cost Contingency | [5 empty] | 1500
Total | [5 empty] | 142863
Hardware Cost per Deployment Region
Hardware | Western Region |  | Ontario Region |  | Québec Region |  | Atlantic Region
| Quantity | Cost | Quantity | Cost | Quantity | Cost | Quantity | Cost
Lenovo ThinkPad T430 Laptop | 25 | 25600 | 25 | 25600 | 25 | 25600 | 25 | 25600
Targus DEFCON Serialized Laptop Locks (25 per Box) | 1 | 650 | 1 | 650 | 1 | 650 | 1 | 650
BenQ BL2201PU 22-inch Monitor | 25 | 4725 | 25 | 4725 | 25 | 4725 | 25 | 4725
Logitech MK120 Desktop Keyboard and Mouse | 25 | 300 | 25 | 300 | 25 | 300 | 25 | 300
Total | 76 | 31275 | 76 | 31275 | 76 | 31275 | 76 | 31275
Assumptions
- It is assumed that the 100 workstations deployments are spread evenly amongst each region. Furthermore, it is assumed that at each region, the necessary furniture, electrical, and networking requirements are in place. - It is assumed that all hardware is purchased and not leased, due to Seacrest Industries' internal policies. - We assume that Seacrest Industries' IT department owns the necessary software licenses for all of their required utilities, and that this project's scope is limited to providing laptops, laptop locks, monitors, keyboards, and mice. - At this time, it is assumed that all products will be purchased directly from CDW Canada, and are already in Canadian Dollars. - Tax is calculated at 13%. - Exact shipping costs cannot be calculated, because they are subject to negotiation once we show the vendor that we are serious about purchasing their products. In some cases, vendors may offer free shipping as an incentive. Nevertheless, an estimate has been made for shipping, and is labelled as the Shipping Cost Contingency, for use in the scenario that we do need to cover the shipping costs. - We assume that all products will arrive in working condition from the vendor, and will function as intended. - Once the included support and warranty period have expired for the hardware, Seacrest Industries will be required to pay for vendor technical support, if required, as Equilibrium Consulting does not perform hardware repairs. - The hardware will be delivered directly to Seacrest Industries' offices in each region.

## Project Lifecycle Costs
Seacrest Industries - November 2013 Workstation Deployment Project Project Lifecycle Costs and Depreciation Rate for Hardware
Project Lifecycle Costs for Hardware
Operating Costs
Hardware | Total Initial Cost | Year 1 | Year 2 | Year 3 | Total Cost for 3 Years
Lenovo ThinkPad T430 Laptop | 115712 | 0 | 847.5 | 118026.24 | 234585.74
Targus DEFCON Serialized Laptop Locks (25 per Box) | 2938 | 0 | 0 | 0 | 2938
BenQ BL2201PU 22-inch Monitor | 21357 | 150 | 150 | 150 | 21807
Logitech MK120 Desktop Keyboard and Mouse | 1356 | 50 | 50 | 50 | 1506
Total |  |  |  |  | 260836.74
Hardware Depreciation
Hardware | Initial Cost per Item | Year 1 Value | Year 2 Value | Year 3 Value | Depreciated Value
Lenovo ThinkPad T430 Laptop | 1024 | 512 | 409.6 | 327.68 | 327.68
Targus DEFCON Serialized Laptop Locks (25 per Box) | 650 | 325 | 260 | 208 | 208
BenQ BL2201PU 22-inch Monitor | 189 | 94.5 | 75.6 | 60.48 | 60.48
Logitech MK120 Desktop Keyboard and Mouse | 12 | 6 | 4.8 | 3.84 | 3.84
Total Hardware Value after 3 Years |  |  |  |  | 40032
Assumptions
- The Total Cost for 3 Years does not include the potential $1,500 shipping cost. - Tax is calculated at 13%, and is subject to change within the timespan of 1-3 years. - There are no regular annual or monthly fees associated with the selected hardware. - It is assumed that of the 100 laptops deployed, that at least 15 of them will need a new battery after 2 years (due to incorrect charging by end users). The cost of a replacement battery is $50.00. - Laptops were selected due to their ease of maintenance (if they break, the manufactuer has a 3 year warranty, exclusing battery replacments), and low cost compared to upgrading traditional desktop computers regularily. As a result, by Year 3, we have provisioned for the cost of replacing all 100 laptops across all regions, at a cost of $1,044.48 per laptop (accounting for 2% inflation). - There is no yearly operational cost assosiated with the laptop locks. - It is assumed that a cost of $150 per year is required for monitor cleaning supplies and replacment display cables. - It is assumed that a cost of $50 per year is required for keyboard and mouse cleaning supplies. - At the end of 3 years, the monitors, keyboards, and mice will still be functional. - All hardware depreciates by 50% within the first year, followed by a 10% decrease each subsequent year.

## Consulting Fees
Seacrest Industries - November 2013 Workstation Deployment Project Consulting Fees
Consulting Fees
Item | Cost | Tax | Total
Solution Design | 4500 | 585 | 5085
Project Implementation Planning | 3000 | 390 | 3390
Required 1 Year Support Contract | 4500 | 585 | 5085
Total |  |  | 13560
Assumptions
- Tax is calculated at 13%. - The optional yearly cost of support after the first mandatory year is $1,500, if Seacrest Industries decides to purchase additional support later on.